## Costs Estimate
Cost Estimate for Development of Alameda Creek Restoration Master Plan
URS Corporation
COST ITEM | Average Hourly Rate / Unit Cost | Field Recon for Updating Reach Descriptions | Task B | Task B | GIS Database | Prepare Outline, Introduction and Background Sections | Description of Goals and Objectives | Prepare Passage Element | Prepare Habitat Element | Implementation Plan | Assemble Draft | Finalize Plan |  | Subtotal Cost | Subtotal Hours
Labor Costs
Prinicpal Professional/Project Director | 160 | [12 empty] | 0 | 0
Senior Project Manager | 150 | 80 |  |  | 16 | 32 | 8 | 60 | 100 | 120 | 24 | 80 |  | 78000 | 520
Project Manager | 135 | [12 empty] | 0 | 0
Senior Project Professional | 115 | [12 empty] | 0 | 0
Senior Archaeologist | 100 | [12 empty] | 0 | 0
Project Professional | 105 |  |  |  |  | 60 | 40 | 100 | 120 | 140 | 24 | 100 |  | 61320 | 584
Archaeologist | 80 | [12 empty] | 0 | 0
Professional | 80 | 240 | [5 empty] | 60 | 100 | 80 |  |  |  | 38400 | 480
Staff Professional | 70 |  |  |  |  | 60 | [7 empty] | 4200 | 60
Sr. Designer/Lab, Field, or CADD Supervisor | 105 | [12 empty] | 0 | 0
Technician | 60 | [12 empty] | 0 | 0
Project Administrator/Controller | 85 | [12 empty] | 0 | 0
CADD/GIS Technician/Illustrator | 80 |  |  |  | 220 | [8 empty] | 17600 | 220
Word Processing/Project Assistant/Editor | 67 |  |  |  |  | 8 | 4 | 24 | 40 | 40 | 40 | 40 |  | 13132 | 196
Clerk | 55 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 990 | 18
Total Labor Hours by Task |  | 322 | 0 | 0 | 238 | 162 | 54 | 246 | 362 | 382 | 90 | 222 | 0 | 2078 | 2078
Total Labor Cost by Task |  | 31310 | 0 | 0 | 20110 | 15946 | 5778 | 26018 | 38390 | 41890 | 8910 | 25290 | 0 | 213642 | 213642
Other Direct Costs (ODCs)
Inhouse reproduction | [10 empty] | 500 | 1200 |  | 1700
Outside Reproduction | [13 empty] | 0
Transportation/Travel/Expenses |  | 250 | [5 empty] | 100 | 150 | 200 |  |  |  | 700
Computer (1) |  |  |  |  | 1200 | [8 empty] | 1200
Communication |  | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs (2) |  | 2200 | [11 empty] | 2200
Subcontractors | [13 empty] | 0
Subtotal ODCs |  | 2450 | 0 | 0 | 1200 | 0 | 0 | 100 | 150 | 200 | 500 | 1200 | 0 | 5800 | 5800
Subcontractor/Outside Expense Markup | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total ODCs |  | 2450 | 0 | 0 | 1200 | 0 | 0 | 100 | 150 | 200 | 500 | 1200 | 0 | 5800
TOTAL BY TASK |  | 33760 | 0 | 0 | 21310 | 15946 | 5778 | 26118 | 38540 | 42090 | 9410 | 26490 | 0
(1) Computer charges only apply to specialized applications including CADD and GIS. Routine day-to-day computer usage not charged. | [13 empty] | 219442 | 219442
(2) Cost for 2 hours of helicopter rental at $1,100/hour